## Risk Register
SalesOps AI — Risk Register
Impact scale: 1=Negligible · 2=Minor · 3=Moderate · 4=Major · 5=Critical Likelihood scale: 1=Rare · 2=Unlikely · 3=Possible · 4=Likely · 5=Almost Certain Risk Score = Impact × Likelihood (max 25)
Risk ID | Category | Risk Title | Description | Impact (1–5) | Impact Label | Likelihood (1–5) | Likelihood Label | Risk Score (1–25) | Priority Band | Owner
R-01 | Infrastructure | AWS Lab Credentials Expire Mid-Session | Temporary AWS Academy credentials expire every few hours. A live deployment or demo can fail completely if credentials lapse during SAM deploy, SQS operation, or Secrets Manager access. | 4 | Major | 5 | Almost Certain | 20 | Critical | DevOps Lead
R-02 | External Dependency | OpenAI API Quota Exceeded During Exam Evaluation | The evaluation Lambda calls OpenAI with no quota guard. High concurrent usage or a low-tier API key can trigger rate-limit errors, leaving reps with no coaching result after completing an exam. | 4 | Major | 4 | Likely | 16 | High | Backend Dev
R-03 | Infrastructure | Cognito User Pool Deleted on CloudFormation Stack Update | Renaming the Cognito resource in template.yaml causes CloudFormation to delete and recreate the User Pool, permanently deleting all user accounts and invalidating all active tokens. | 5 | Critical | 3 | Possible | 15 | High | DevOps Lead
R-06 | External Dependency | OpenAI Model Deprecated or API Schema Change | The backend hardcodes the OpenAI Responses API endpoint and JSON schema. A model deprecation or API version change would silently break issue generation and evaluation without code changes. | 4 | Major | 3 | Possible | 12 | Medium | Backend Dev
R-08 | Data Integrity | Demo Issues Delivered to Reps Without Manager Awareness | When OpenAI fails during issue generation the backend silently stores demo issues. If the manager does not check the generationWarning field, reps take exams on scripted dummy content without knowing. | 3 | Moderate | 4 | Likely | 12 | Medium | Backend Dev
R-12 | Security | Refresh Token Exposure Enables Long-Lived Session Hijack | Refresh tokens are valid for 30 days and are stored in browser local storage without HttpOnly protection. XSS on the frontend or local storage inspection can expose the token to an attacker. | 4 | Major | 3 | Possible | 12 | Medium | Security Lead
R-04 | Performance | DynamoDB Full-Table Scan Degrades Under Load | The dashboard, persona list, scenario list, and exam scenario list all use Scan. Under heavy load or a large dataset the scan latency can exceed Lambda timeouts and degrade the manager experience. | 3 | Moderate | 3 | Possible | 9 | Medium | Backend Dev
R-07 | Security | CORS Wildcard Origin Allows Unauthorized Frontend | The current CORS configuration allows any origin. Any web page can make credentialed calls to the API if it possesses a valid Cognito token, widening the attack surface for token-stealing exploits. | 3 | Moderate | 3 | Possible | 9 | Medium | Security Lead
R-11 | Operations | Manager Archives All Scenarios Before a Scheduled Exam | The archive action has no confirmation guard in the backend. A manager can accidentally archive all published scenarios, making the exam list empty for all reps until scenarios are republished. | 4 | Major | 2 | Unlikely | 8 | Medium | Project Manager
R-05 | Reliability | SQS Delayed Message Not Delivered During Exam | If the SQS delivery for an exam issue is late or dropped, the issue will not become visible on time. The pulse endpoint mitigates this but only when polled; issues may still appear late. | 3 | Moderate | 2 | Unlikely | 6 | Low | Backend Dev
R-10 | Reliability | Exam Clock Skew Causes Premature or Late Issue Release | Issue release timing is calculated server-side using Lambda clock. Large clock skew between Lambda invocations or between SQS and Lambda can cause issues to be revealed out of order or late. | 3 | Moderate | 2 | Unlikely | 6 | Low | Backend Dev
R-09 | Data Integrity | DynamoDB Item Size Limit Exceeded by Large Scenario | All generated issues are stored inside one DynamoDB item on the Scenarios table. At the maximum 20 issues with long messages the item may approach or exceed DynamoDB's 400 KB item size limit. | 2 | Minor | 2 | Unlikely | 4 | Low | Backend Dev

## Priority Matrix
Risk Priority Matrix — Likelihood vs Impact
| 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Critical
5 Almost Certain | 5 | 10 | 15 | R-01 | 25
4 Likely | 4 | 8 | R-08 | R-02 | 20
3 Possible | 3 | 6 | R-04, R-07 | R-06, R-12 | R-03
2 Unlikely | 2 | R-09 | R-05, R-10 | R-11 | 10
1 Rare | 1 | 2 | 3 | 4 | 5
Legend:
Critical |  | Score 20–25
High |  | Score 13–19
Medium |  | Score 7–12
Low |  | Score 1–6

## Top Risk Mitigation
Detailed Mitigation Plan — R-01: AWS Lab Credentials Expire Mid-Session
Risk ID | R-01
Category | Infrastructure
Risk Title | AWS Lab Credentials Expire Mid-Session
Description | Temporary AWS Academy credentials expire every few hours. A live deployment or demo can fail completely if credentials lapse during SAM deploy, SQS operation, or Secrets Manager access.
Impact | 4 – Major
Likelihood | 5 – Almost Certain
Risk Score | 20 / 25 (Critical)
Owner | DevOps Lead / Project Manager
Root Cause | AWS Academy provides temporary STS credentials that expire every 4-8 hours. The project requires these credentials for every SAM deploy, Lambda invocation test, DynamoDB CLI operation, and Secrets Manager rotation. There is no automated refresh mechanism in the repository — the developer must manually copy new credentials before each session.
Impact Detail | If credentials expire during a SAM deployment, CloudFormation may enter a partial update state requiring manual rollback. If they expire during an exam demo, SQS and DynamoDB operations will fail with AuthorizationError, ending the exam session abruptly. Any Lambda invocation requiring Secrets Manager (issue generation, evaluation) will also fail, leaving reps without scoring results.
Mitigation — Immediate | 1. Add a pre-session checklist to the admin guide requiring credential refresh before every lab session. 2. Add a startup script (scripts/check-creds.sh) that runs `aws sts get-caller-identity` and exits with an error message if credentials are expired or missing. 3. Display a credential expiry warning in the README and admin guide with the exact refresh procedure.
Mitigation — Short Term | 1. Wrap the SAM deploy npm script to call `aws sts get-caller-identity` first and abort if it fails. 2. Add a GitHub Actions workflow step that validates credentials before any deploy step. 3. Store credential refresh instructions as a pinned note in the team project board.
Mitigation — Long Term | 1. Migrate from AWS Academy to a dedicated AWS account where long-lived IAM roles with instance profiles eliminate per-session credential rotation entirely. 2. Use AWS CLI named profiles with SSO to allow automated token refresh without manual copy-paste. 3. Implement infrastructure-level monitoring (CloudWatch alarm on Lambda auth errors) to alert the team immediately when credentials expire unexpectedly during a session.
Residual Risk After Mitigation | Impact reduced to 2 (Minor) — automated pre-session check catches the issue before it affects end users. Likelihood reduced to 3 (Possible) — manual step still required in Academy environment. Residual Score: 2 × 3 = 6 (Low).
Acceptance Criteria | Risk is considered mitigated when: (a) credential check script exists and passes in CI, (b) admin guide section 08 includes the refresh checklist, (c) no deployment has failed due to expired credentials in the last 3 lab sessions.